COMMUNITY EDUCATIONAL PROJECT

Student name

University

Professor’s name

Submission date

Addressing Physical Activity in Adolescence

1: Project plan

- Goals and Objectives based on healthy people 2030:

Goal: Increase physical activity among adolescents

Objective 1: By the end of six months, increase the percentage of adolescents engaging in at least 60 minutes of physical activity from 30% to 50%

Objective 2: Improve awareness about the importance of physical activity, leading to a 20% increase in knowledge among adolescents within three months

Goal: Establish sustainable physical activity programs in schools

Objective 1: Collaborate with local schools to implement daily physical activity breaks within three months.

Objective 2: Provide training for school staff on integrating physical activity into the curriculum, archiving 80% participation within six months.

- Implementation Plan

Activities:

Conduct workshop for adolescents on the benefits of physical activity.

Distribute informational materials promoting physical activities

Partner with schools to incorporate physical activity breaks

Provide training session for school staff

Timeline:

Month 1-2: Develop educational materials and plan workshops.

Month3-4: Implement workshop and distribute materials.

Month 5-6: Initiate physical activity breaks in school and conduct training for staff.

c)Budget (if necessary)

Workshop materials: $1,000

Printing information materials: $800

Training sessions: $2,000

d)Justification of the Project

Increasing physical activity aligns with healthy People 2030 goals and addresses rising concerns about sedentary lifestyles in adolescent, reducing the risk of chronic diseases.

e) Description of where and when the plan will be implemented

Schools within the community; workshops during school hours, physical activity during designated school periods.

f) Teaching materials

Brochures, posters and interactive presentations highlighting benefits of physical activity.

2.Reccommended nursing Action/Interventions:

Promote health education by collaborating with school nurses to integrate health education into the curriculum.

Monitor progress by implementing regular assessment to track changes in physical activity levels

3: Public and private partnership.

Public partnership:

Collaborate with the local health department to access resources and expertise.

Private partnership:

Partner with local businesses for sponsorship or donations of equipment.

4)Prevention implementation plan.

Activities:

Establish community sports club

Engage parents through informational sessions.

Create after-school programs focusing in active recreation.

Timeline:

Month1-3: Form partnership and plan community sessions.

Month4-6: Launch sports club and after-school programs.

5) Expected outcome

Increased awareness and participation in physical activity.

Establishment of sustainable programs in schools.

Improved overall health and well-being of adolescents.